## QA Summary
DEV Changes QA Tracker
One worksheet per QA module. Use each module’s Status dropdown, then return here for the live roll-up. Attach evidence or a defect link for every failure or blocker.
Total Cases | 133 | Passed | 50 | Failed | 0 | Blocked | 1 | Complete % | 38.35% | Build | DEV - 2026-08-02
Module | Total | Pass | Fail | Blocked | In Progress | Not Started | N/A | Complete % | Owner | Overall Status | Notes
Test Setup | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 100% |  | Complete
Resource Onboarding | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 100% |  | Complete
Workspace Switching | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 100% |  | Complete
Deployment | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 100% |  | Complete
Inspection Completion | 11 | 9 | 0 | 1 | 1 | 0 | 0 | 90.91% |  | Blocked
Invoice Lifecycle | 14 | 7 | 0 | 0 | 0 | 7 | 0 | 50% |  | Not Started
Gusto Payouts | 11 | 0 | 0 | 0 | 0 | 11 | 0 | 0% |  | Not Started
Scheduler Regression | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0% |  | Not Started
Employees Owners | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0% |  | Not Started
Service Model | 17 | 0 | 0 | 0 | 0 | 17 | 0 | 0% |  | Not Started
Help Center | 7 | 0 | 0 | 0 | 0 | 7 | 0 | 0% |  | Not Started
Notifications Email | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0% |  | Not Started
Cleanup Smoke | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0% |  | Not Started
Exit Criteria | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0% |  | Not Started

## Test Setup
Test Setup QA | [9 empty] | ← QA Summary
Prepare representative users, properties, billing data, and rates before executing workflow tests.
Total | 10 | Passed | 10 | Failed | 0 | Blocked | 0 | Completion | 100% | Update Status in column G
Test ID | Priority | Scenario | Preconditions | Test Steps | Expected Outcome | Status | Tester | Test Date | Evidence / Defect Link | Notes
SET-01 | P0 | Platform administrator account | DEV environment is reachable. | Confirm an active platform administrator can sign in. | Platform administration, Resources & Payables, service billing, and request-review areas are accessible. | Pass | Mitch | 2026-08-03 |  | account user is dev@afterlightinspections.com
SET-02 | P0 | Organization administrator account | A test organization exists. | Confirm an organization administrator can sign in to the organization workspace. | Organization administration and service-model request features are accessible without platform-only permissions. | Pass | mitch | 2026-08-03 |  | account user is mitchfurrier@gmail.com
SET-03 | P0 | Assigned property manager | Property A belongs to the test organization. | Assign a property manager to Property A and confirm sign-in. | The manager can access Property A review flows and cannot access unassigned properties. | Pass | Mitch | 2026-08-03 |  | account user is highspeedmitch@gmail.com
SET-04 | P0 | Dual-workspace submitter | An existing organization submitter email is available. | Record the submitter identity for later contractor linking. | The same identity can be used to verify organization/resource workspace switching without duplication. | Pass | Mitch | 2026-08-03 |  | account user is skylinemitch@outlook.com
SET-05 | P0 | New contractor email | Use an email that has never signed in to DEV. | Record the address for contractor invitation testing. | The address is ready for a resource-only onboarding path. | Pass | Mitch | 2026-08-03 |  | account user is Al1099Dev@yahoo.com
SET-06 | P1 | Employee or owner resource | An employee or owner relationship can be created. | Create or identify an active employee/owner resource. | The resource is available for non-contractor scheduling and payable-exclusion tests. | Pass | Mitch | 2026-08-03 |  | AlEmployee1@proton.me
SET-07 | P1 | Ordinary organization user | A non-admin, non-manager organization account exists. | Confirm the user can sign in. | The account is ready for permission-denial checks. | Pass | Mitch | 2026-08-03 |  | gunguymitch@gmail.com
SET-08 | P0 | Property A billing configuration | Property A is managed or hybrid and eligible for deployment. | Set a billing code, customer amount, assigned property manager, and accounts-payable email. | Property A is fully configured for assignment, invoice, review, and AP delivery tests. | Pass | Mitch | 2026-08-03 |  | Property is Winterhaven Square
SET-09 | P1 | Property B exclusion case | Property B is in the same test organization. | Leave the contractor undeployed to Property B. | Property B can prove property-scoped resource eligibility. | Pass | Mitch | 2026-08-03
SET-10 | P0 | Rate fixtures | A contractor profile is available. | Set the contractor default to $75 and prepare a Property A override of $90. | Tests can verify rate overrides and immutable assignment snapshots. | Pass | Mitch | 2026-08-03 |  | rate is set to $75 on al1099dev

## Resource Onboarding
Resource Onboarding QA | [9 empty] | ← QA Summary
Validate contractor linking, invitations, eligibility gates, activation, and suspension behavior.
Total | 8 | Passed | 8 | Failed | 0 | Blocked | 0 | Completion | 100% | Update Status in column G
Test ID | Priority | Scenario | Preconditions | Test Steps | Expected Outcome | Status | Tester | Test Date | Evidence / Defect Link | Notes
ONB-01 | P0 | Open Resources & Payables | Signed in as a platform administrator. | Open Resources & Payables. | Profiles, deployments, earnings, and payout batches are visible and load without errors. | Pass | Mitch | 2026-08-03 |  | account is dev@afterlightinspections.com
ONB-02 | P0 | Link an existing submitter | Existing organization submitter is not yet a contractor. | Add the submitter email as a contractor. | The existing identity is linked; no duplicate user or unnecessary invitation is created. | Pass | Mitch | 2026-08-03 |  | account is skylinemitch@outlook.com
ONB-03 | P0 | Reject duplicate contractor email | The submitter is already linked as a contractor. | Attempt to add the same email again. | The duplicate is rejected with a clear message and no second profile is created. | Pass | Mitch | 2026-08-03 |  | duplicate account was attempted on al1099dev@yahoo.com and failed succesfully
ONB-04 | P0 | Invite a new contractor | Unused email is available. | Add the new email as a contractor. | An invitation is created and the account begins as resource-only unless separately linked to an organization. | Pass | Mitch | 2026-08-03 |  | al1099dev@yahoo.com,
ONB-05 | P0 | Block premature activation | Contractor onboarding is incomplete in Gusto. | Attempt to mark the contractor Active. | Activation is refused and the UI identifies the missing Gusto prerequisite. | Pass | Mitch | 2026-08-03 |  | Confirmed system failure notification that Gusto onboarding must be complete before resource ativation
ONB-06 | P0 | Complete Gusto onboarding and activate | Contractor profile exists and is inactive. | Mark Gusto onboarding Completed, then mark the profile Active. | The contractor becomes active and previously entered profile/rate values remain intact. | Pass | Mitch | 2026-08-03 |  | confirmed success
ONB-07 | P1 | Reject ineligible identity link | Use an inactive, admin-only, or property-manager-only account. | Attempt to link the account as a contractor. | The link is rejected without changing either identity or role memberships. | Pass | Mitch | 2026-08-03 |  | Confirmed inelligible. May need to update error to state that they are inelligible due to already existing as role with elevated permissions
ONB-08 | P0 | Suspend a resource profile | A dual-workspace contractor is active. | Suspend the profile, then reauthenticate. | Resource entitlement is removed on the next authentication while historical assignments and earnings remain available to authorized admins. | Pass | Mitch | 2026-08-03

## Workspace Switching
Workspace Switching QA | [9 empty] | ← QA Summary
Verify identity-safe navigation between organization and resource workspaces.
Total | 6 | Passed | 6 | Failed | 0 | Blocked | 0 | Completion | 100% | Update Status in column G
Test ID | Priority | Scenario | Preconditions | Test Steps | Expected Outcome | Status | Tester | Test Date | Evidence / Defect Link | Notes
WRK-01 | P0 | Expose resource workspace after reauthentication | Existing submitter has been linked as an active contractor. | Sign out and sign back in. | The Resource Portal option appears for the same identity. | Pass | Mitch | 2026-08-03 |  | Tested with Skylinemitch@Outlook.com
WRK-02 | P0 | Switch organization to resource | Dual-workspace account is in the organization workspace. | Use the workspace switcher to open Resource Portal. | The portal opens under the same identity with only resource-authorized data. | Pass | Mitch | 2026-08-03 |  | Tested with Skylinemitch@Outlook.com
WRK-03 | P0 | Switch resource to organization | Dual-workspace account is in Resource Portal. | Switch back to the organization workspace. | The correct organization role and access are restored. | Pass | Mitch | 2026-08-03 |  | Tested with Skylinemitch@Outlook.com
WRK-04 | P1 | Hide switcher for organization-only user | User has no resource profile. | Sign in and inspect global navigation. | No Resource Portal switch option is shown. | Pass | Mitch | 2026-08-03
WRK-05 | P0 | Restrict resource-only account | New contractor has no organization membership. | Attempt to enter an organization workspace directly. | Access is denied or redirected safely to Resource Portal. | Pass | Mitch | 2026-08-03
WRK-06 | P0 | Safe fallback after suspension | A dual-workspace resource profile has been suspended. | Reauthenticate and attempt to open Resource Portal. | Resource access is denied and the user safely falls back to their authorized organization workspace. | Pass | Mitch | 2026-08-03

## Deployment
Deployment QA | [9 empty] | ← QA Summary
Validate resource deployment, property eligibility, scheduling, assignment visibility, and compensation snapshots.
Total | 10 | Passed | 10 | Failed | 0 | Blocked | 0 | Completion | 100% | Update Status in column G
Test ID | Priority | Scenario | Preconditions | Test Steps | Expected Outcome | Status | Tester | Test Date | Evidence / Defect Link | Notes
DEP-01 | P0 | Deploy contractor to Property A | Contractor is active; Property A is managed or hybrid. | Create an active deployment scoped to Property A. | The deployment saves and shows the correct organization, property, dates, and active status. | Pass | Mitch | 2026-08-03 |  | AL 1099 Resource
DEP-02 | P0 | Apply property rate override | Contractor default is $75. | Set the Property A override to $90. | The deployment shows $90 while the contractor default remains $75. | Pass | Mitch | 2026-08-03 |  | AL 1099 Resource
DEP-03 | P0 | Show deployed contractor in scheduler | Active deployment exists for Property A. | Open Property A scheduling and choose the Afterlight contractor source. | The contractor appears as an eligible resource. | Pass | Mitch | 2026-08-03
DEP-04 | P0 | Exclude contractor from Property B | Contractor is not deployed to Property B. | Open Property B scheduling. | The contractor does not appear and cannot be assigned by a crafted request. | Pass | Mitch | 2026-08-03
DEP-05 | P0 | Pause or end deployment | A deployment is active. | Pause or end it, then create a future assignment. | The resource is unavailable for future scheduling outside the active deployment window. | Pass | Mitch | 2026-08-03
DEP-06 | P1 | Respect resource unavailability | Resource is deployed but marked unavailable for the target date. | Attempt to schedule the resource. | The resource is excluded or the assignment is rejected with an availability message. | Pass | Mitch | 2026-08-03
DEP-07 | P0 | Create single-day assignment | Resource is eligible for Property A. | Create an assignment with a start date and no end date. | The assignment saves and is displayed as a single-day assignment. | Pass | Mitch | 2026-08-03
DEP-08 | P0 | Display assignment card details | Assignment exists for the contractor. | Open Resource Portal and inspect the card. | Organization, property, dates, instructions, and $90 compensation are displayed correctly. | Pass | Mitch | 2026-08-03
DEP-09 | P0 | Preserve assignment compensation snapshot | An assignment was created at $90. | Change the contractor/deployment rate after assignment creation. | The existing assignment still shows $90; only later assignments use the new rate. | Pass | Mitch | 2026-08-03
DEP-10 | P1 | Enforce deployment date boundaries | Deployment has explicit start and end dates. | Try assignments immediately before, within, and after the range. | Only dates within the active range are accepted. | Pass | Mitch | 2026-08-03

## Inspection Completion
Inspection Completion QA | [9 empty] | ← QA Summary
Exercise contractor inspection execution, security, retry safety, PDF persistence, and earning creation.
Total | 11 | Passed | 9 | Failed | 0 | Blocked | 1 | Completion | 90.91% | Update Status in column G
Test ID | Priority | Scenario | Preconditions | Test Steps | Expected Outcome | Status | Tester | Test Date | Evidence / Defect Link | Notes
INS-01 | P0 | Start inspection from assignment | An active contractor assignment is visible. | Open the assignment card and start the inspection. | The correct checklist loads with the expected assignment and property identity. | Pass | Mitch | 2026-08-03 |  | account tested in gunguymitch@gmail.com
INS-02 | P1 | Display assignment instructions | Assignment includes custom instructions. | Open the inspection experience. | Instructions are complete, readable, and associated with the correct assignment. | Pass | Mitch | 2026-08-03 |  | account tested in gunguymitch@gmail.com
INS-03 | P0 | Block missing required field | Inspection checklist is open. | Leave a required field blank and submit. | Submission is blocked and the missing field is clearly identified. | Pass | Mitch | 2026-08-03 |  | account tested in gunguymitch@gmail.com
INS-04 | P0 | Upload photos once | Valid photos are available. | Attach photos and submit while observing progress/retry states. | Uploads use the secure path, progress is visible, and no duplicate asset is created. | Pass | Mitch | 2026-08-03 |  | account tested in gunguymitch@gmail.com
INS-05 | P0 | Complete assigned inspection | All required data is valid. | Submit the inspection. | The inspection reaches Complete and a completion confirmation is shown. | Pass | Mitch | 2026-08-03 |  | account tested in gunguymitch@gmail.com
INS-06 | P0 | Remove completed assignment from active portal | Inspection completed successfully. | Return to or refresh Resource Portal. | The completed assignment is no longer listed as active work. | Pass | Mitch | 2026-08-03 |  | account tested in gunguymitch@gmail.com
INS-07 | P0 | Prevent duplicate completion on retry | A completion response is delayed or retried. | Refresh/retry the completion request. | Only one inspection, PDF, invoice, and earning are associated with the assignment. | Blocked
INS-08 | P0 | Reject property or URL tampering | Resource has an assignment only for Property A. | Alter a property/assignment identifier in the URL or request. | The request is denied and no unauthorized property data is exposed. | Pass | Mitch | 2026-08-03 |  | account tested in gunguymitch@gmail.com
INS-09 | P0 | Persist completion when SES fails | Email delivery is configured to fail. | Complete an otherwise valid inspection. | Inspection and PDF persist; delivery failure is recorded and no duplicate is produced. | In Progress | Mitch | 2026-08-03
INS-10 | P0 | Create one contractor earning | Contractor assignment has $90 snapshot. | Inspect Resources & Payables after completion. | Exactly one $90 earning exists in Pending Approval for the contractor. | Pass | Mitch | 2026-08-03 |  | al1099dev@yahoo.com
INS-11 | P0 | Exclude employee/owner from payable creation | Employee/owner assignment is available. | Complete the same workflow as an employee/owner. | The inspection completes but no contractor earning is created. | Pass | Mitch | 2026-08-03 |  | skylinemitch@outlook.com

## Invoice Lifecycle
Invoice Lifecycle QA | [9 empty] | ← QA Summary
Validate customer invoice preparation, review, revisions, AP delivery, and independent payment state.
Total | 14 | Passed | 7 | Failed | 0 | Blocked | 0 | Completion | 50% | Update Status in column G
Test ID | Priority | Scenario | Preconditions | Test Steps | Expected Outcome | Status | Tester | Test Date | Evidence / Defect Link | Notes
INV-01 | P0 | Auto-create customer invoice | Afterlight commercial inspection completes with billing fully configured. | Complete the inspection and open service billing. | One platform-owned invoice and PDF are created in Awaiting Review. | Pass | Mitch |  |  | Al1099dev@yahoo.com
INV-02 | P0 | Verify invoice PDF fields | Invoice PDF exists. | Open the PDF and compare it with property, service, and performer data. | Billing code, amount, property, service details, and performer are correct; Afterlight is the invoice owner. | Pass | Mitch |  |  | Al1099dev@yahoo.com
INV-03 | P0 | Deny billing access to resource | Signed in as the contractor performer. | Attempt to open Billing or the invoice directly. | Billing access is denied without exposing customer amounts. | Pass | Mitch |  |  | al1099dev@yahoo.com
INV-04 | P0 | Allow only assigned manager review | Assigned and unassigned property-manager accounts exist. | Open the invoice as each manager. | Assigned manager can review; unassigned manager is denied. | Pass | Mitch |  |  | Al1099dev@yahoo.com
INV-05 | P1 | Require decline reason | Invoice is Awaiting Review. | Choose Decline without a reason. | The action is rejected and invoice status does not change. | Pass | Mitch |  |  | Invoice BLK01-1785815140114
INV-06 | P0 | Decline with reason | Invoice is Awaiting Review. | Decline and enter a reason. | Status becomes Needs Revision and the reason appears in Platform Service Billing. | Pass | Mitch |  |  | Invoice BLK01-1785815140114
INV-07 | P0 | Invalidate stale PDF after amount change | Invoice needs revision. | Change the customer amount as a platform administrator. | The prior PDF is invalidated and cannot be resent as the current invoice. | Pass | Mitch
INV-08 | P0 | Regenerate and resend revision | Invoice amount has changed. | Regenerate the PDF and resend for review. | The new amount and PDF are used and status returns to Awaiting Review. | Not Started
INV-09 | P0 | Approve and send to AP | Invoice is valid and awaiting assigned-manager review. | Approve and send it to accounts payable. | Status becomes Sent to AP and the expected attachment is delivered. | Not Started
INV-10 | P0 | Handle invalid AP address safely | Set an invalid AP email. | Attempt AP delivery. | Status records AP Delivery Failed while the invoice and inspection remain intact. | Not Started
INV-11 | P0 | Retry AP delivery without duplication | An AP delivery has failed. | Correct the email and retry. | Delivery succeeds using the same invoice; no duplicate invoice is created. | Not Started
INV-12 | P0 | Keep payout and invoice payment independent | Invoice and contractor earning both exist. | Mark the contractor payout paid. | Customer invoice remains unpaid and unchanged. | Not Started
INV-13 | P0 | Mark customer invoice paid independently | Customer invoice is sent or payable. | Mark the customer invoice paid. | Only customer invoice state changes; contractor earning/batch state is unchanged. | Not Started
INV-14 | P1 | Surface missing billing configuration | Remove amount, billing code, manager, or AP data in separate runs. | Complete an inspection for each missing field. | Submission succeeds but the invoice shows a visible draft/preparation exception identifying the missing configuration. | Not Started

## Gusto Payouts
Gusto Payouts QA | [9 empty] | ← QA Summary
Validate earning approval, voids, payout batching, submission, payment, and onboarding safeguards.
Total | 11 | Passed | 0 | Failed | 0 | Blocked | 0 | Completion | 0% | Update Status in column G
Test ID | Priority | Scenario | Preconditions | Test Steps | Expected Outcome | Status | Tester | Test Date | Evidence / Defect Link | Notes
PAY-01 | P0 | Approve pending earning | A contractor earning is Pending Approval. | Approve the earning. | Status becomes Approved and it becomes eligible for batching. | Not Started
PAY-02 | P1 | Void eligible earning with reason | Use a Pending Approval or Approved earning. | Void the earning and provide a reason. | Status becomes Void and the reason is retained in audit history. | Not Started
PAY-03 | P0 | Create batch from approved earnings | Multiple Approved earnings are selected. | Create a Gusto batch. | Batch count and total match the selected eligible earnings. | Not Started
PAY-04 | P0 | Exclude unapproved earning from batch | At least one earning is not Approved. | Attempt to include it in a batch. | The earning is refused or excluded and the batch totals remain correct. | Not Started
PAY-05 | P0 | Generate dated grouped payout batch | Approved earnings for one or more contractors exist. | Create the batch with a check date. | A date-stamped batch number is created, earnings are grouped by contractor, and state becomes payout_pending. | Not Started
PAY-06 | P0 | Protect batched earning from void | Earning belongs to an active payout batch. | Attempt to void it. | The action is refused so batch totals cannot silently change. | Not Started
PAY-07 | P0 | Record Gusto submission reference | Batch is Ready for submission. | Record the external submission reference. | Batch becomes Submitted and the reference is retained. | Not Started
PAY-08 | P1 | Cancel Mark Paid confirmation | A submitted batch is open. | Start Mark Paid, then cancel. | No batch or earning status changes. | Not Started
PAY-09 | P0 | Confirm Mark Paid | A submitted batch is open. | Confirm Mark Paid. | Batch and all included earnings become Paid exactly once. | Not Started
PAY-10 | P0 | Reject invalid contractor payout identity | Contractor has missing/mismatched email or incomplete onboarding. | Attempt to create/submit a batch containing the earning. | The batch action is refused with an actionable validation message. | Not Started
PAY-11 | P0 | Keep contractor amount independent | Customer invoice amount differs from contractor compensation. | Compare earning, batch, and invoice values. | Payout uses the assignment compensation snapshot, not the customer invoice amount. | Not Started

## Scheduler Regression
Scheduler Regression QA | [9 empty] | ← QA Summary
Protect mobile layout, date handling, conflict rules, completed-assignment behavior, and role-based resource sources.
Total | 10 | Passed | 0 | Failed | 0 | Blocked | 0 | Completion | 0% | Update Status in column G
Test ID | Priority | Scenario | Preconditions | Test Steps | Expected Outcome | Status | Tester | Test Date | Evidence / Defect Link | Notes
SCH-01 | P1 | Use scheduler at 390px | Browser dev tools or a 390px device is available. | Open and exercise the scheduler at 390px width. | Controls remain usable and the page has no unintended horizontal scrolling. | Not Started
SCH-02 | P0 | Correct invalid end date | Scheduler create/edit form is open. | Set a start date after the current end date. | The invalid end date is cleared or corrected and cannot be saved incorrectly. | Not Started
SCH-03 | P0 | Create multi-day assignment | Eligible resource and property exist. | Set valid start and end dates and save. | The exact date range is persisted and displayed. | Not Started
SCH-04 | P0 | Edit single-day assignment | A single-day assignment exists. | Open edit mode. | Start date is populated and end date remains blank. | Not Started
SCH-05 | P0 | Drag assignment to new date | Draggable scheduled assignment exists. | Drag it to a valid date and refresh. | Persisted dates match the new calendar position. | Not Started
SCH-06 | P0 | Reject schedule conflict | Resource already has a conflicting active assignment. | Attempt an overlapping assignment. | The conflict is rejected without modifying the existing assignment. | Not Started
SCH-07 | P0 | Allow reuse after completion | Same resource/property/date combination was completed. | Schedule that combination again. | The new assignment succeeds and no obsolete uniqueness constraint blocks it. | Not Started
SCH-08 | P0 | Protect completed assignment | A completed assignment exists. | Attempt to edit or delete it. | The action is refused or safely constrained so completed inspection history is preserved. | Not Started
SCH-09 | P0 | Enforce manager property scope | Property manager is not assigned to Property B. | Attempt to schedule Property B. | Property B is hidden or the write is rejected. | Not Started
SCH-10 | P1 | Filter fulfillment sources | Employee/owner and contractor resources exist. | Switch between staff and contractor fulfillment sources. | Employee/owner appears only under the staff source and contractor only under the contractor source. | Not Started

## Employees Owners
Employees Owners QA | [9 empty] | ← QA Summary
Verify non-contractor resources can be deployed and scheduled without creating payables.
Total | 5 | Passed | 0 | Failed | 0 | Blocked | 0 | Completion | 0% | Update Status in column G
Test ID | Priority | Scenario | Preconditions | Test Steps | Expected Outcome | Status | Tester | Test Date | Evidence / Defect Link | Notes
PPL-01 | P0 | Create employee or owner resource | Platform administrator is signed in. | Add an employee/owner resource without Gusto data or a contractor rate. | The relationship saves without requiring contractor payout fields. | Not Started
PPL-02 | P0 | Deploy and schedule staff | Employee/owner resource is active. | Deploy and schedule through the Afterlight staff source. | The resource appears in the correct source and can be assigned to eligible property/dates. | Not Started
PPL-03 | P0 | Complete staff inspection without payable | Employee/owner assignment exists. | Complete the inspection. | Customer invoicing may proceed, but no contractor earning is created. | Not Started
PPL-04 | P1 | Show relationship instead of earnings | Employee/owner signs into the resource experience. | Inspect portal summary/details. | The employment/owner relationship is shown without contractor earning amounts. | Not Started
PPL-05 | P1 | Hide contractor payout guidance | Employee/owner is signed in. | Open contextual help. | Contractor earnings/Gusto guidance is hidden or replaced with appropriate non-payable guidance. | Not Started

## Service Model
Service Model QA | [9 empty] | ← QA Summary
Validate governed service-model changes, review decisions, notifications, versioning, and future-only effects.
Total | 17 | Passed | 0 | Failed | 0 | Blocked | 0 | Completion | 0% | Update Status in column G
Test ID | Priority | Scenario | Preconditions | Test Steps | Expected Outcome | Status | Tester | Test Date | Evidence / Defect Link | Notes
SVC-01 | P1 | Show current model read-only | Organization administrator is signed in. | Open service-model settings. | Current model and effective details are visible but cannot be edited directly. | Not Started
SVC-02 | P0 | Submit service-model request | No active request exists. | Choose a different model, provide reason/effective date, and submit. | A Pending request is created while the current model remains unchanged. | Not Started
SVC-03 | P1 | Notify active platform administrators | Multiple active platform admins exist. | Submit the request. | All active platform admins receive an informative notification/email. | Not Started
SVC-04 | P0 | Reject second active request | A request is already Pending or awaiting organization response. | Submit another request. | The second active request is rejected without overwriting the first. | Not Started
SVC-05 | P0 | Deny request permission | Sign in as a property manager or ordinary user. | Attempt to submit a model-change request. | Access is denied and no request is created. | Not Started
SVC-06 | P1 | Show complete platform review details | Pending request exists. | Open the platform review queue. | Organization, current/requested model, reason, effective date, requester, and history are complete. | Not Started
SVC-07 | P1 | Require note for Request Info | Pending request exists. | Choose Request Info without a note. | Action is rejected and request status remains unchanged. | Not Started
SVC-08 | P0 | Request info with note | Pending request exists. | Provide a note and submit Request Info. | Status changes appropriately and the organization is notified with the note. | Not Started
SVC-09 | P0 | Organization responds to info request | Request is awaiting organization response. | Submit the requested response. | Request returns to platform review and active platform admins are notified. | Not Started
SVC-10 | P1 | Require denial note | Pending request exists. | Choose Deny without a note. | Action is rejected and policy remains unchanged. | Not Started
SVC-11 | P0 | Deny with note | Pending request exists. | Provide a denial note and confirm. | Request is denied, current model remains unchanged, and history/notification include the note. | Not Started
SVC-12 | P0 | Approve request atomically | Pending request matches current policy version. | Approve it. | Model/defaults update, property overrides clear, policy version increments, and status/history/notification update together. | Not Started
SVC-13 | P0 | Preserve historical work | Assignments/invoices predate approval. | Compare them after approval. | Existing assignments and invoices retain their original model and monetary snapshots. | Not Started
SVC-14 | P0 | Apply new defaults prospectively | Model change is approved. | Create a new eligible assignment. | The new assignment uses the newly approved defaults. | Not Started
SVC-15 | P0 | Reject stale approval | Current model/version changed after request creation. | Attempt to approve the stale request. | Approval is refused and no newer policy state is overwritten. | Not Started
SVC-16 | P0 | Reject direct organization update | Organization administrator can craft API requests. | Attempt a direct model update, including with a passkey. | The update is rejected; only the governed review path can change policy. | Not Started
SVC-17 | P1 | Display decision history | Prior approved/denied/request-info decisions exist. | Open service-model history. | Chronological decisions, notes, actors, dates, and versions are visible. | Not Started

## Help Center
Help Center QA | [9 empty] | ← QA Summary
Verify audience-specific help content, contextual links, and article completeness.
Total | 7 | Passed | 0 | Failed | 0 | Blocked | 0 | Completion | 0% | Update Status in column G
Test ID | Priority | Scenario | Preconditions | Test Steps | Expected Outcome | Status | Tester | Test Date | Evidence / Defect Link | Notes
HLP-01 | P1 | Open public contractor setup article | Signed out. | Open the public contractor setup help URL. | The intended public article loads without exposing private application data. | Not Started
HLP-02 | P1 | Show contractor guidance | Signed in as a contractor. | Open Help Center. | Resource workflow and earnings/Gusto guides are visible. | Not Started
HLP-03 | P1 | Tailor employee/owner guidance | Signed in as an employee/owner resource. | Open Help Center. | Resource workflow help is visible while contractor earnings guidance is absent. | Not Started
HLP-04 | P1 | Show platform guidance | Signed in as platform administrator. | Open Help Center. | Platform, Gusto, service billing, and review guides are visible. | Not Started
HLP-05 | P1 | Restrict organization-admin help | Signed in as organization administrator. | Open Help Center. | Organization guidance is visible and platform-only operational content is hidden. | Not Started
HLP-06 | P1 | Open contextual help links | Scheduler, Resources, Service Billing, and Service Delivery pages are available. | Open each contextual help link. | Each link lands on the relevant article and preserves a usable return path. | Not Started
HLP-07 | P1 | Load complete article catalog | Help Center is reachable. | Open all 16 articles. | Every article loads with no missing assets, broken navigation, or console errors. | Not Started

## Notifications Email
Notifications Email QA | [9 empty] | ← QA Summary
Verify recipient routing and ensure delivery failures never roll back primary business records.
Total | 6 | Passed | 0 | Failed | 0 | Blocked | 0 | Completion | 0% | Update Status in column G
Test ID | Priority | Scenario | Preconditions | Test Steps | Expected Outcome | Status | Tester | Test Date | Evidence / Defect Link | Notes
NTF-01 | P0 | Notify resource without org membership | Resource-only contractor is deployed and assigned. | Create/send the assignment notification. | The resource receives the notification despite having no organization membership. | Not Started
NTF-02 | P0 | Send successful SES attachments | SES is functioning and an inspection/report/invoice is ready. | Complete the workflow and inspect received messages. | Correct recipients receive the expected report and invoice attachments. | Not Started
NTF-03 | P0 | Keep completion after SES failure | SES is intentionally invalid. | Complete an inspection. | Completion and PDFs persist, an error is recorded, and retry does not duplicate artifacts. | Not Started
NTF-04 | P0 | Keep service request after email failure | Service-model email delivery is configured to fail. | Submit or update a service-model request. | The in-app request/history persists and the delivery problem is visible. | Not Started
NTF-05 | P1 | Notify all active platform admins | Multiple active and inactive platform admins exist. | Create/update a service-model request. | All active platform admins are notified; inactive accounts are not treated as recipients. | Not Started
NTF-06 | P0 | Route completion notifications correctly | Contractor assignment exists for Property A. | Complete the inspection. | Notifications reference the correct resource portal, organization, property, and assignment. | Not Started

## Cleanup Smoke
Cleanup Smoke QA | [9 empty] | ← QA Summary
Confirm the authentication, route, Mapbox, and dependency cleanup did not remove live behavior.
Total | 10 | Passed | 0 | Failed | 0 | Blocked | 0 | Completion | 0% | Update Status in column G
Test ID | Priority | Scenario | Preconditions | Test Steps | Expected Outcome | Status | Tester | Test Date | Evidence / Defect Link | Notes
CLN-01 | P0 | Use live client assignment route | Authorized user and valid client/property fixtures exist. | Call /api/client/assign-client through the supported UI/API path. | The supported route succeeds with the expected authorization and response. | Not Started
CLN-02 | P0 | Exercise AzRoots property routes | Authorized AzRoots test data exists. | Run the supported property GET and PUT workflows. | Both operations succeed with no authentication regression. | Not Started
CLN-03 | P0 | Load consolidated payments summary | User has submissions, assignments, and mileage/payment history. | Open/call the consolidated payments summary. | Response includes submissions, assignments, current mileage, YTD mileage, and YTD payments. | Not Started
CLN-04 | P0 | Retire admin user-submissions route | Use an authenticated admin request. | Call /admin/user-submissions/:id. | Endpoint returns 404 and no duplicate legacy handler responds. | Not Started
CLN-05 | P0 | Retire admin assign-client route | Use an authenticated admin request. | Call /admin/assign-client-to-property. | Endpoint returns 404; the supported client route remains functional. | Not Started
CLN-06 | P0 | Retire mileage user route | Use an authenticated request. | Call /api/mileage/user/:id. | Endpoint returns 404; consolidated mileage/payment data remains available. | Not Started
CLN-07 | P1 | Remove global Mapbox resources | Browser cache is disabled or cleared. | Load the application and inspect network/document styles. | Global Mapbox GL and Directions CSS resources are absent. | Not Started
CLN-08 | P0 | Preserve geocoding behavior | A workflow using address geocoding is available. | Search/resolve a valid address. | Geocoding still returns and applies the expected result. | Not Started
CLN-09 | P1 | Avoid duplicate authentication work | Client and AzRoots routes are instrumented/logged. | Make one authorized request to each. | Each request completes under one authenticated session with no duplicate authentication errors or repeated side effects. | Not Started
CLN-10 | P0 | Run full navigation smoke | Representative platform, organization, and resource accounts exist. | Exercise login, dashboards, billing, and Help Center. | Core pages load with no new browser console errors or backend exceptions. | Not Started

## Exit Criteria
Exit Criteria QA | [9 empty] | ← QA Summary
Release gates that must be satisfied before the DEV change set is promoted.
Total | 8 | Passed | 0 | Failed | 0 | Blocked | 0 | Completion | 0% | Update Status in column G
Test ID | Priority | Scenario | Preconditions | Test Steps | Expected Outcome | Status | Tester | Test Date | Evidence / Defect Link | Notes
EXT-01 | P0 | All P0 cases pass | All module testing is complete. | Review P0 rows across the workbook. | Every applicable P0 row is Pass; any exception is formally accepted and linked. | Not Started
EXT-02 | P0 | No cross-tenant access | Permission and tampering tests are complete. | Review evidence for organization, property, and resource boundaries. | No account accessed another tenant/property/assignment outside its authorization. | Not Started
EXT-03 | P0 | Amounts remain independent | Invoice and earning tests are complete. | Compare contractor compensation and customer billing across workflows. | Contractor amounts and customer invoice amounts never overwrite or derive from one another incorrectly. | Not Started
EXT-04 | P0 | Retries remain idempotent | Retry/failure-path testing is complete. | Review inspection, PDF, invoice, and earning record counts. | No retry created duplicate inspections, PDFs, invoices, or earnings. | Not Started
EXT-05 | P0 | Completed assignments can be scheduled again | Scheduler regression tests are complete. | Review completed-combination reuse evidence. | A new assignment can reuse a previously completed resource/property/date combination. | Not Started
EXT-06 | P0 | Service policy changes are future-only | Service-model approval tests are complete. | Compare pre- and post-approval records. | Historical assignments/invoices remain unchanged and only new work uses the new policy. | Not Started
EXT-07 | P0 | Email failures are non-destructive | SES failure tests are complete. | Review primary records and delivery errors. | Business records persist and failures are observable/retryable without duplication. | Not Started
EXT-08 | P0 | No new uncaught errors | Full smoke and targeted tests are complete. | Review browser console and backend logs. | No new uncaught frontend errors, unhandled promise rejections, or backend exceptions remain. | Not Started